## Risk log
Risk Register
Project name: | Glazes Project risks
Project manager: Bob | Jazmyne Kingi
[14 empty] | Likelihood | 0 | 0
[14 empty] | 1 | 2 | 3
ID | Date raised | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions | Status | Useful resources | Impact | 1 | Low | Low | Medium
1 | [start] | Project management, Scope creep, lack of communication, unreseolved conflicts | Low | High | High | Project manager | Implement a formal change control board and daily stand up meetings to ensure clarity. |  | Business case re-written with clear deliverables and submitted to the project board for approval. | Open | https://elogic.co/blog/ecommerce-project-manager-responsibilities-explained/ | 0 | 2 | Low | Medium | High
2 | [start] | Operational and supply chain, Vendor delays, manufacturing disruptions, logistical bottlenecks | High | High | High | Operations manager, supply chain lead | Diversify vendors to avoid single-point failures and maintain "buffer stick" for critical componets |  | Design workshops scheduled. | Open | https://www.shipbob.com/blog/ecommerce-operations/ | 0 | 3 | Medium | High | High
3 | [start] | IT and Security, Data breaches, ransomeware and systems outages | Low | High | Medium | IT manager | Deploy multi-factor authentication, regular encrypted back ups and employee phishing training |  | Workshops scheduled. | Open | https://www.fortinet.com/resources/cyberglossary/it-security
4 | [enter date] | Finance and compliance, Late tax, international payment and regulatory checks. | High | Low | Medium | Finance manager | Use automated compliance software and enforce segregation of duties for all finacial transactions. |  | Project Sponsor has agreed to hold briefing. Now making arrangements for a meeting room. | Open | https://www.stakeholdermap.com/project-dictionary/project-dictionary-p.html#project-sponsor
5 | [enter date] | Human Resources, to anticipate issues such as turn overs, labor disputes or worker shortages. | Low | Medium | High | HR manager CISO | cross-training all team members on critical tasks to ensure informativable. |  | Lead time from each contractor built into the project schedule. Late penalties agreed to and contracts signed. | Open | https://acquirex.io/blog/human-resource-management-secrets-for-ecommerce-success/
6 | [enter date] | Eternal threats, Acts of weather, legal action, theift. | High | High | High | Project sponsor | Break this risk into two: 'cost estimating' and 'scheduling errors'. Use two methods of cost estimation, and carefully track costs and forecast cost at completion making adjustments as necessary. Build in 10% contingency on cost and scheduling. Track schedules daily and include schedule review as an agenda item in every project team meeting. Flag forecast errors and/or delays to the Project Board early. |  | Contingency agreed by Project Board. | Open | https://phoenixnap.com/blog/ecommerce-security-threats

## Severity Table
Likelihood
|  | 1 | 2 | 3 | 0 | 0 | Likelihood | 0 | 0
Impact | 1 | Low | Low | Medium | 0 | 0 | 1 | 2 | 3
| 2 | Low | Medium | High | Impact | 1 | Low | Low | Medium
| 3 | Medium | High | High | 0 | 2 | Low | Medium | High
[5 empty] | 0 | 3 | Medium | High | High

## Dropdowns
Likelihood | Impact | Status
[select] | [select] | Open
High | High | In progress
Medium | Medium | Closed
Low | Low